## Slide 1
HIPPOCRATIC AI
CONFIDENTIAL | Q2 2026
Rebuilding for the Long Term:
A Partnership Turnaround Plan
WellLife Health System | Quarterly Business Review | April 2026
Presented by: Kelly Williams
VP, Customer Success — Hippocratic AI

## Slide 2
01
EXECUTIVE SUMMARY
Where We Stand — and Why This QBR Matters
9 Months In
Partnership launched with strong early momentum
55% Adoption
Only half of planned departments fully live
Renewal On Hold
Pending outcome of this QBR
Our Objectives Today
✦ Acknowledge what isn't working — with full transparency
✦ Present a concrete, time-bound turnaround plan
✦ Re-establish clear ownership and accountability
✦ Align on measurable success milestones for the next 90 days
Our Commitment
WellLife chose Hippocratic AI to extend your care team's reach — to connect more patients, reduce staff burden, and improve access. That mission has not changed. What needs to change is how we show up as a partner every single day. That work starts today.

## Slide 3
02
ROOT CAUSE ANALYSIS
Four Interconnected Failure Points
01
Implementation Drift
Workflow configurations were not mapped to department-level scheduling rules before go-live. Phase 2 expanded scope faster than validation could keep up, leaving gaps between how the voice agent behaves and how each department actually operates.
02
Governance Breakdown
Local script modifications were made by WellLife ops teams outside of the agreed governance review process. Without a shared change-control framework, both sides lost visibility — creating a cycle of friction, workarounds, and eroding trust.
03
Platform Reliability Gap
A recent platform update introduced latency and voice quality issues that were not caught in pre-release testing. Repeated escalations — paused responses, looping questions — directly damaged frontline staff confidence in a clinical-facing tool.
04
CS Model Failure
Reactive, siloed support with no single owner left WellLife stakeholders feeling handed off between teams. The absence of proactive communication — especially around updates, known issues, and roadmap — signaled to the client that they were not a priority.

## Slide 4
03
STRATEGIC PLAN
90-Day Turnaround Roadmap
PHASE 1
Days 1–30
STABILIZE
• Assign dedicated Client Success Pod with named owner
• Complete full workflow audit across all live departments
• Deploy hotfix for latency/voice quality; establish regression testing
• Institute 48-hr ticket SLA with escalation path to CS lead
• Weekly executive check-ins with WellLife leadership
PHASE 2
Days 31–60
ALIGN
• Co-design department-specific workflow playbooks with WellLife ops
• Launch joint governance committee (Hippocratic AI + WellLife IT + Clinical Ops)
• Introduce roadmap co-input sessions — WellLife priorities reflected in Q3 plan
• Rebuild script library using approved, governed templates
• Present mid-point progress report with metrics dashboard
PHASE 3
Days 61–90
ACCELERATE
• Expand from 55% → 85%+ department adoption with validated configs
• Launch proactive communication cadence: release previews, issue alerts
• Establish QBR rhythm: monthly operational + quarterly strategic
• Re-open renewal conversation with full confidence data package
• Present 180-day expansion roadmap for new service lines

## Slide 5
04
ENGAGEMENT MODEL
One Team. One Owner. No Handoffs.
Dedicated WellLife Client Pod
VP, Customer Success
Executive sponsor & escalation owner. Single point of accountability.
Clinical Success Partner
Embedded in WellLife clinical ops. Workflow alignment & adoption.
Technical Solutions Engineer
Owns platform performance, bug resolution & config governance.
Support Lead
Dedicated queue. 48-hr SLA. Proactive issue communication.
Operating Cadence
Weekly
Operational Sync
CS Lead + WellLife Access Center & IT
Bi-Weekly
Clinical Workflow Review
Clinical Success Partner + Dept Leads
Monthly
Executive Briefing
VP CS + WellLife SVP + Hippocratic AI Exec
Quarterly
Strategic QBR
Full leadership + outcomes + roadmap
On Demand
Escalation Bridge
<2hr response, named owner, no handoffs

## Slide 6
05
SUCCESS METRICS
How We'll Know It's Working
Platform Reliability
Voice latency
Now: < 400ms avg
Goal: < 300ms
Uptime SLA
Now: < 99%
Goal: 99.9%
Ticket resolution
Now: > 72 hrs
Goal: < 24 hrs
Post-update regressions
Now: Unmonitored
Goal: Zero tolerance process
Adoption & Utilization
Dept. adoption rate
Now: 55%
Goal: 85% by Day 90
Agent task completion
Now: Baseline TBD
Goal: +20% vs. baseline
Manual override rate
Now: Elevated
Goal: < 10% per dept
Staff training completion
Now: Partial
Goal: 100% live depts
Relationship & Trust
WellLife NPS (internal)
Now: Negative / neutral
Goal: Net positive by Day 90
Exec sentiment score
Now: Concern
Goal: Confident
Proactive comms sent
Now: Reactive only
Goal: Weekly cadence live
Renewal discussion
Now: On hold
Goal: Reopened by Day 75
Business Outcomes
Patient connection rate
Now: Baseline
Goal: +15% vs. pre-engagement
Call center deflection
Now: Baseline
Goal: +25% by Day 90
Staff overtime (PAC)
Now: Elevated
Goal: Returning to pre-pilot
Expansion pipeline
Now: Paused
Goal: 1 new service line scoped

## Slide 7
06
QBR NARRATIVE
How We Frame This Conversation
OPEN: Acknowledge & Own
"Before we go to slides — I want to acknowledge that the last several months have not reflected the partnership you were promised. Workflow gaps, technical issues, and feeling passed around without clear ownership: those are real, and they are on us. I am not here to explain them away. I am here to show you exactly what we are doing about it."
MIDDLE: Show the Plan with Confidence
"We have done a full audit. We know where the breakdowns happened and why. What you will see today is not a list of intentions — it is a 90-day plan with named owners, measurable milestones, and a governance model that prevents these issues from recurring. We want you to hold us to every single one of these commitments."
CLOSE: Reframe as Partnership
"WellLife took a bold step partnering with Hippocratic AI. You believed that AI-powered voice agents could genuinely extend your care teams reach and improve patient access. We believe that too — and we have seen it work in your own early pilots. The goal of this QBR is to get back to that promise — together. We are asking for 90 days and your continued candor. In return, you will have a partner who shows up every week, not just when something breaks."